*Organizing Checklist/ Timeline*

*This is a tool for you to use however you want; an editable Word version is also available for downloading on the mgol.net website to modify in whatever way will be most helpful to you.*

|  |  |
| --- | --- |
| ***3 – 6 Months Ahead***   * Determine who will be Hatchlings administrator and facilitators for the programs * Decide on times and dates in collaboration with library branch(es)/community partner location(s)and schedule appropriate staff * Schedule location/technology availability for in-person, virtual only, and/or hybrid programming options * Determine take-home kit procedures (pick-up and/or delivery before, during, after program options) * and create a plan for distribution * Determine which additional language versions will be needed, e.g., Spanish; secure translator to prepare surveys, handouts, promotional materials * Ensure that publicity data / event information is entered into computer databases and flyers/signage is ordered * Work with communications department/staff to arrange for any special publicity or signage needs, * such as press releases, social media, special distribution, and, inclusion in email blasts * Check catalog, as appropriate, to determine materials to highlight for the program; work with * materials management department if program requires the purchase of materials * Determine hands-on activity materials needed and refreshments to purchase, if appropriate | ***1 – 2 Months Ahead***   * Determine who will be responsible for on-site/virtual needs, such as room set-up, facilitating the program, and providing technical support, if needed. * Schedule virtual platform (Zoom, StreamYard, etc.), reserve equipment, and schedule staff (tech producers, greeters, & others) * Finalize plans with Hatchlings administrator, facilitators, community partners, and anyone else involved in the program. * Hatchlings administrator/facilitators and community partners finalize plans * Confirm schedules for all staff and sponsors * Confirm on-site needs as appropriate, such as set-up, presenter introduction, sponsors, etc. * Collate materials into kits ready for pick-up, and delivery   ***2 - 3 Weeks Before a Program***   * Confirm final details with team * Use social media for promotional push (Instagram, Facebook, etc.) * Check registration lists for upcoming programs. Confirm registrants using email, phone, What’s App, etc. to begin building relationships and remind them of the upcoming program. * Use email, phone, WhatsApp etc. to begin building relationships with registrants and remind them of the upcoming program. * Track and manage take-home kit distribution to branches for pickup or delivery to partners/individual homes |

|  |  |
| --- | --- |
| ***1 Week Before a Program***   * Confirm with team for last-minute details, including confirmation of prepared consent forms and evaluations * Confirm arrangements, arrival time with branch staff/community partners * Confirm staff/community partner assignments such as set-up, tech producer, etc. * Confirm presenter materials, kits for in-program activities, refreshments, if appropriate * Send email reminders/phone call/WhatsApp reminders to all confirmed registrants   ***Program Day***   * Program facilitator will meet with on-site contact/staff to work through any last-minute details * Use materials checklist to ensure that all necessary forms are available * Implement program, including room set-up and tear-down; all materials are in order and are displayed as appropriate * Count attendance * Take photos as appropriate | ***After the Program***   * Enter program statistics; work with Elaine Czarnecki, our evaluator, re: consent forms, surveys. (ecz.read@gmail.com) * Partner with Maryland State Library to help track consent forms, surveys, and sign-in sheets * Jot down observations, quotes, anecdotes for final report. * Send a “thank you” to those involved (if deemed appropriate) * Send best photos to Carrie Sanders at the Maryland State Library Agency ([carrie.sanders@maryland.gov](mailto:carrie.sanders@maryland.gov)) |